## User Stories
Customer selection | 0-Mandatory 1-Essential(MVP) 2-Could Include 3-Outside Scope 4-Unacheavable or Unnecessary | Comment | 18 | < - Planned Veloicty Planned User Stories -> | 15.25 |  | Business Value | Prerequisites | Notes | Mitchell |  | Andre |  | Troy |  | Max |  | Faye |  | Jayden |  | Samantha |  | Paul |  | Group Average (Time blocks) | complexity | Weighted Averge (Product Sum Average) | Time | Maximum | Minimum | Variance | Planned (sub total)
|  |  | FINDING COURSES THAT FIT CRITERIA - DATABASE INTEGRATION | [6 empty] | Rankings for next lab | [15 empty] | Basic Statistics
| Priority | ID |  | AS A | I Want To | So That |  |  | Notes | Don't forget Testing as part of your estimates
|  | US |  | User | be able search courses by keywords or other criteria | I can find the courses I need/want to take |  |  | Core Feature. Too general -> Expanded to several similar below | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence | Time Blocks | Confidence
|  | ID |  | AS A | I Want To | So That
| 1 | US: | 1 | User | be able to search courses based on their course name | I can find specific courses faster |  | 12,46 |  | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 4 | 2 | 4 | 2 | 5 | 3 | 3 | 2 | 4 | 2 | 4.375 | 1.9429 | 2 | 3 | 1 | 0.28571 | 0
|  | ID |  | Given | When | Then
|  | AT | 1.1 | app on course search screen | I enter a string in the search field | only courses with names matching that string are shown in the window below
|  | AT | 1.2 | app on course search screen | enter a string in the search field and no matches | no matches displayed on screen
|  | AT | 1.3 | app on course search screen | enter a string that only appears in other terms | give a notification that matching entries found in other terms
|  | AT | 1.4
|  | ID |  | AS A | I Want To | So That
| 1 | US: | 2 | User | to be able to search courses based on their course code | I can find specific courses faster |  | 12,46 |  | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 4 | 1 | 5 | 2 | 4 | 1 | 4 | 2 | 4 | 1.625 | 4.5 | 1.6111 | 1.5 | 2 | 1 | 0.26786 | 0
|  | ID |  | Given | When | Then
|  | AT | 2.1 | app on course search screen | I enter a course code (4 letters, 4 numbers or both) | only show courses matching that code potion or full code
|  | AT | 2.2 | app on course search screen | I enter a course code that no part matches | gives a notification that no matches found
|  | AT | 2.3 | app on course search screen | I enter a code that isn't available this term | gives a notification that course not offered this term
|  | AT | 2.4
|  | ID |  | AS A | I Want To | So That
| 1 | US: | 3 | User | be able to search courses based on their CRN | I can find specific courses faster |  | 12,46 |  | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 4 | 1 | 5 | 2 | 4 | 1 | 4 | 2 | 4 | 1.625 | 4.5 | 1.6111 | 1.5 | 2 | 1 | 0.26786 | 0
|  | ID |  | Given | When | Then
|  | AT | 3.1 | app on course search screen | I enter an existing CRN number | only shows courses matching that CRN
|  | AT | 3.2 | app on course search screen | I enter an non-existing CRN number | gives a notification that no courses matched
|  | AT | 3.3 | app on course search screen | enter a no longer relevant CRN | give notification that that crn s not valid on this term
|  | AT | 3.4
|  | ID |  | AS A | I Want To | So That
| 2 | US: | 4 | User | be able to search courses based on faculty | I can choose electives/other courses reevant to me |  | 12,46 |  | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 4 | 2 | 4 | 1 | 5 | 1 | 4 | 2 | 4 | 1.625 | 4.5 | 1.6111 | 1.5 | 2 | 1 | 0.26786 | 0
|  | ID |  | Given | When | Then
|  | AT | 4.1 | course search screen | select from drop down menu | lists courses of that faculty
|  | AT | 4.2
|  | AT | 4.3
|  | AT | 4.4
|  | ID |  | AS A | I Want To | So That
| 2 | US: | 5 | User | be able to search courses based on their time slot | I can find courses that fit my schedule |  | 12,46 |  | 3 | 5 | 4 | 4 | 1 | 5 | 2 | 4 | 2 | 4 | 3 | 4 | 1 | 4 | 3 | 4 | 2.375 | 4.25 | 2.3529 | 2.25 | 4 | 1 | 1.125 | 0
|  | ID |  | Given | When | Then
|  | AT | 5.1 | app on course search screen | I enter a start and end time in the time fields | I display courses that only fall in those times |  |  | This could include labs / tutorials as well.
|  | AT | 5.2 | app on course search screen | I enter a start and end time in the time fields that dont make sense | I get a warning message.
|  | AT | 5.3
|  | AT | 5.4
|  | ID |  | AS A | I Want To | So That
| 2 | US: | 6 | User | be able to search courses based on their day(s) of the week | I can find courses that fit my schedule |  | 12,46 |  | 2 | 5 | 3 | 4 | 1 | 5 | 2 | 4 | 2 | 5 | 2 | 4 | 1 | 5 | 2 | 4 | 1.875 | 4.5 | 1.8333 | 1.75 | 3 | 1 | 0.41071 | 0
|  | ID |  | Given | When | Then
|  | AT | 6.1 | app on course search screen | I select the boxes for days of the week | I see only courses that fall (only) on those days
|  | AT | 6.2
|  | AT | 6.3
|  | AT | 6.4
|  | ID |  | AS A | I Want To | So That
| 3 | US: | 7 | User | be able to search courses based on their professor | I can avoid the garbage fire that is most of Dalhousie |  | 12,46 |  | 2 | 5 | 4 | 4 | 1 | 5 | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 5 | 2 | 4 | 2 | 4.375 | 1.9429 | 2 | 4 | 1 | 0.85714 | 0
|  | ID |  | Given | When | Then
|  | AT | 7.1
|  | AT | 7.2
|  | AT | 7.3
|  | AT | 7.4
|  | ID |  | AS A | I Want To | So That
| 3 | US: | 8 | User | be able to search courses based on their availability (waitlist) | I can find courses that I can register for now |  | 12,46 |  | 2 | 5 | 3 | 3 | 1 | 5 | 2 | 4 | 2 | 4 | 3 | 3 | 1 | 5 | 2 | 4 | 2 | 4.125 | 1.8788 | 2 | 3 | 1 | 0.57143 | 0
|  | ID |  | Given | When | Then
|  | AT | 8.1
|  | AT | 8.2
|  | AT | 8.3
|  | AT | 8.4
|  | ID |  | AS A | I Want To | So That
| 3 | US: | 9 | User | be able to search courses based on their location (Campus) | I can find courses I can actually get to |  | 12,46 |  | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 4 | 2 | 4 | 2 | 3 | 1 | 5 | 2 | 4 | 1.75 | 4.375 | 1.7143 | 1.75 | 2 | 1 | 0.21429 | 0
|  | ID |  | Given | When | Then
|  | AT | 9.1
|  | AT | 9.2
|  | AT | 9.3
|  | AT | 9.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 10 | User | be able to view my favorited classes | I can quickly register |  | 12,14,45, 46 |  | 3 | 5 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 4 | 5 | 3 | 3 | 3 | 3.625 | 3.069 | 3 | 4 | 2 | 0.28571 | 0
|  | ID |  | Given | When | Then
|  | AT | 10.1
|  | AT | 10.2
|  | AT | 10.3
|  | AT | 10.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 11 | User | see classes that don't conflict with my registerd courses | I can quickly fill up my schedule |  | 12,18,45 ,46 |  | 4 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | 3.25 | 3.25 | 3.3077 | 3.25 | 4 | 3 | 0.21429 | 0
|  | ID |  | Given | When | Then
|  | AT | 11.1
|  | AT | 11.2
|  | AT | 11.3
|  | AT | 11.4
VIEWING SPECIFIC COURSE INFO (FOR A SINGLE COURSE) - DATABASE INTEGRATION
|  | ID |  | AS A | I Want To | So That
1 | 0 | US | 12 | User | View Course information | I can decide if I Want To to register / find the class / go on to register |  | 46 | This one is pretty general as well. We could divide it into the types of info (Example the waitlist could be a portion of this) | 5 | 5 | 2 | 5 | 1 | 5 | 1 | 4 | 2 | 4 | 2 | 2 | 4 | 4 | 4 | 4 | 2.625 | 4.125 | 2.6667 | 2.75 | 5 | 1 | 2.2679 | 2.75
|  | ID |  | Given | When | Then
|  | AT | 12.1 | course search results | user clicks on a course | user is brought to a course description page
|  | AT | 12.2 | course search results | user is viewing results | detailed information is displayed
|  | AT | 12.3
|  | AT | 12.4
|  | ID |  | AS A | I Want To | So That
1 | 0 | US | 13 | User | be able to see how many spots remain in a course | register / waitlist |  | 12, 46 | I suggest having just a little color coded fill up bar. but to start we could just post numbers | 2 | 5 | 3 | 5 | 1 | 5 | 1 | 4 | 2 | 5 | 1 | 4 | 2 | 3 | 2 | 4 | 1.75 | 4.375 | 1.7714 | 1.75 | 3 | 1 | 0.5 | 1.75
|  | ID |  | Given | When | Then
|  | AT | 13.1 | course search results | browsing search results | a section showing how many students are registered as well as capacity is displayed
|  | AT | 13.2 | student course schedule | view course details | one of the details listed displays course capacity
|  | AT | 13.3
|  | AT | 13.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 14 | User | mark a course as favorite | it appears in my favorites section for quick access |  | 12, 45 |  | 2 | 5 | 4 | 5 | 3 | 3 | 3 | 3 | 2 | 4 | 1 | 4 | 2 | 4 | 2 | 4 | 2.375 | 4 | 2.375 | 2.5 | 4 | 1 | 0.83929 | 0
|  | ID |  | Given | When | Then
|  | AT | 14.1 | a course description screen | user clicks "favorite button" | course is added to favorite courses
|  | AT | 14.2 | course search results | user clicks "favorite button" | course is added to favorite courses
|  | AT | 14.3
|  | AT | 14.4
REGISTER FOR A COURSE - UNIVERSITY INTEGRATION
|  | ID |  | AS A | I Want To | So That
| 0 | US | 15 | User | be notified if there is a conflict between my selected courses | I can work out a schedule that works |  | 12, 18, 45,46 | this could easily move to after our abiity to register | 3 | 3 | 2 | 4 | 1 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 2 | 3 | 2.625 | 3.5 | 2.5357 | 2.5 | 4 | 1 | 0.83929 | 0
|  | ID |  | Given | When | Then
|  | AT | 15.1 | registration page | crn is entered and a conflict occurs | notification of conflict
|  | AT | 15.2 | search results page | user presses "registration button" | notification of conflict
|  | AT | 15.3
|  | AT | 15.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 16 | User | be abe to overide the conflict message | I can take the course anyway |  | 12, 18, 45,46 |  | 3 | 5 | 6 | 4 | 1 | 5 | 2 | 3 | 4 | 3 | 1 | 5 | 3 |  | 2 | 3 | 2.75 | 4 | 2.6071 | 2.5 | 6 | 1 | 2.7857 | 0
|  | ID |  | Given | When | Then
|  | AT | 16.1 | registration page | conflict notification popup | option to undo changes or dismiss message
|  | AT | 16.2 | search results page | conflict notification popup | option to undo changes or dismiss message
|  | AT | 16.3
|  | AT | 16.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 17 | User | be able to login ( Not to actual University) | complete the registration rpocess |  | 46 | This isn't necessary for the project | 8 | 3 | 5 | 5 | 10 | 1 | 5 | 3 | 7 | 2 | 5 | 2 | 6 | 2 | 8 | 1 | 6.75 | 2.375 | 6.2105 | 6.25 | 10 | 5 | 3.3571 | 0
|  | ID |  | Given | When | Then
|  | AT | 17.1 | login page | user enters valid net id and valid password | user is brought to main menu
|  | AT | 17.2 | login page | user enters valid net id and invalid (or blank) password | error message/try again
|  | AT | 17.3 | login page | user enters invalid (or blank) net id and valid password | error message/try again
|  | AT | 17.4 | login page | user enters invalid (or blank) net id and invalid (or blank) password | error message/try again
|  | ID |  | AS A | I Want To | So That
1 | 0 | US | 18 | User | register for a course | I can take that course |  | 12, 46 | we could complete this without having completed the calendar view | 3 | 3 | 2 | 4 | 1 | 5 | 3 | 4 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2.375 | 3.375 | 2.2963 | 2.25 | 3 | 1 | 0.55357 | 2.25
|  | ID |  | Given | When | Then
|  | AT | 18.1 | registration page | crn is entered by user | course is added to course list
|  | AT | 18.2 | course search results | "register button" is pressed by the user | course is added to course list
|  | AT | 18.3 | course description page | "register button" is pressed by the user | course is added to course list
|  | AT | 18.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 19 | User | see program requirments (for graduation) | I can see what I need to complete |  | Not doing this | This might mean incorporating their degree audit system. Definitely outside the scope of this course | 40 | 5 | 35 | 4 | 10 | 1 | 6 | 4 | 20 | 3 | 10 | 1 | 10 | 2 | 10 | 1 | 17.625 | 2.625 | 22.5714 | 22.5 | 40 | 6 | 167.9821 | 0
|  | ID |  | Given | When | Then
|  | AT | 19.1
|  | AT | 19.2
|  | AT | 19.3
|  | AT | 19.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 20 | User | be added to the waitlist if the course is full and waitlist opens | I can eventually get in the course |  | 12, 13,18, 45, 46 |  | 10 | 3 | 15 | 5 | 5 | 3 | 8 | 2 | 8 | 2 | 10 | 1 | 6 | 2 | 8 | 1 | 8.75 | 2.375 | 9.5789 | 9.5 | 15 | 5 | 9.3571 | 0
|  | ID |  | Given | When | Then
|  | AT | 20.1
|  | AT | 20.2
|  | AT | 20.3
|  | AT | 20.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 21 | User | mark a course as interested and be notified when a full waitlist opens up a slot | I can be added to the waitlist |  | 12, 13,18, 45, 46 |  | 6 | 3 | 20 | 4 | 5 | 2 | 5 | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 5 | 1 | 6.75 | 2.25 | 8.2778 | 8.25 | 20 | 2 | 30.2143 | 0
|  | ID |  | Given | When | Then
|  | AT | 21.1
|  | AT | 21.2
|  | AT | 21.3
|  | AT | 21.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 22 | User | be automatically added to the waitlist if it frees up | I don't have to register myself |  | same as above | I think this is the same as 20 | 10 | 3 | 10 | 4 | 10 | 1 | 10 | 1 | 10 | 1 | 10 | 1 | 10 | 1 | 10 | 1 | 10 | 1.625 | 10 | 10 | 10 | 10 | 0 | 0
|  | ID |  | Given | When | Then
|  | AT | 22.1
|  | AT | 22.2
|  | AT | 22.3
|  | AT | 22.4
DROP A COURSE - UNIVERSITY INTEGRATION
|  | ID |  | AS A | I Want To | So That
1 | 2 | US | 23 | User | drop a course | I can make room for a different one |  | 1946-12-18 |  | 3 | 3 | 2 | 5 | 1 | 5 | 1 | 4 | 2 | 4 | 1 | 4 | 2 | 5 | 2 | 4 | 1.75 | 4.25 | 1.7059 | 1.75 | 3 | 1 | 0.5 | 1.75
|  | ID |  | Given | When | Then
|  | AT | 23.1
|  | AT | 23.2
|  | AT | 23.3
|  | AT | 23.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 24 | User | be notified if dropping a course will auto drop other courses | I don't unintentioaally drop a course |  | 23* |  | 7 | 3 | 2 | 5 | 1 | 5 | 2 | 4 | 5 | 4 | 5 | 3 | 5 | 4 | 5 | 3 | 4 | 3.875 | 3.6774 | 3.75 | 7 | 1 | 4.2857 | 0
|  | ID |  | Given | When | Then
|  | AT | 24.1
|  | AT | 24.2
|  | AT | 24.3
|  | AT | 24.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 25 | User | be asked to confirm to drop a course | i don't do so unintentionally |  | 23* |  | 2 | 5 | 1 | 5 | 1 | 5 | 1 | 4 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1.125 | 4.875 | 1.1282 | 1.25 | 2 | 1 | 0.125 | 0
|  | ID |  | Given | When | Then
|  | AT | 25.1 | my course schedule
|  | AT | 25.2
|  | AT | 25.3
|  | AT | 25.4
CALENDAR VIEW & INTEGRATION
|  | ID |  | AS A | I Want To | So That
| 0 | US | 26 | User | be able to see my weekly schedule | I can modify my schedule / go to class |  | 12, 18, 45, 46, 47 | we could start with only showing after we register, and later make it so that we can plan what we will register for | 4 | 3 | 5 | 5 | 2 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 5 | 3 | 5 | 2 | 4 | 3.5 | 3.8929 | 4 | 5 | 2 | 1.1429 | 0
|  | ID |  | Given | When | Then
|  | AT | 26.1 | main menu | clicks schedule (different views?) | schedule is displayed |  |  | I think we should default to the calendar view upon login. everythign is reached wrt this page
|  | AT | 26.2 | login screen | I submit correct login info | I am taken to the calendar page
|  | AT | 26.3 | any subscreen | press the back / cancel button | I am taken to the calendar page
|  | AT | 26.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 27 | User | be able to export my calendar to my google calendar etc | I can see my schedule outside this ap |  | 26* | This is a nice extended Feature for outside the scope of this project | 8 | 3 | 20 | 4 | 3 | 5 | 6 | 1 | 8 | 2 | 10 | 2 | 6 | 4 | 8 | 1 | 8.625 | 2.75 | 8.7727 | 8.75 | 20 | 3 | 25.4107 | 0
|  | ID |  | Given | When | Then
|  | AT | 27.1
|  | AT | 27.2
|  | AT | 27.3
|  | AT | 27.4
PLANNING AND GROUP FUNCTIONS (SAVE / LOAD / GROUP REGISTER )
|  | ID |  | AS A | I Want To | So That
1 | 2 | US | 28 | User | be able to create an account | I can access saved data later |  | 46 |  | 2 | 3 | 4 | 3 |  |  | 3 | 3 | 3 | 2 | 2 | 3 | 2 |  | 3 | 3 | 2.7143 | 2.8333 | 2.8235 | 2.75 | 4 | 2 | 0.57143 | 2.75
|  | ID |  | Given | When | Then
|  | AT | 28.1 | the sign up / login screen | select creat account | im given username / email / submit fields
|  | AT | 28.2 | sign up info submit view | I press submit and email taken | given a warning
|  | AT | 28.3 | sign up info submit view | I press submit and username taken | given a warning
|  | AT | 28.4 | sign up info submit view | both fields taken | given a warning
|  | AT | 28.5 | sign up info submit view | both fields vaied | creates new user (send email)
|  | ID |  | AS A | I Want To | So That
1 | 2 | US | 29 | User | login to my account | I can access my account |  | 28* |  | 2 | 5 | 4 | 3 |  |  | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 5 | 3 | 3 | 2.2857 | 3.5714 | 2.16 | 2.25 | 4 | 1 | 0.90476 | 2.25
|  | ID |  | Given | When | Then
|  | AT | 29.1
|  | AT | 29.2
|  | AT | 29.3
|  | AT | 29.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 30 | User | be able to add a course to my calendar without registering for it | I can plan my schedule before registering |  | 26* | This is a nice extended Feature for outside the scope of this project | 3 | 3 | 3 | 2 | 10 | 2 | 8 | 2 | 8 | 3 | 3 | 1 | 10 |  | 7 | 2 | 6.5 | 2.1429 | 6.1333 | 6.25 | 10 | 3 | 9.4286 | 0
|  | ID |  | Given | When | Then
|  | AT | 30.1
|  | AT | 30.2
|  | AT | 30.3
|  | AT | 30.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 31 | User | be able to register for all courses in my calendar at once | I do not have to redo the work of finding the classes and setting the schedule |  | 26*, 18* | This is a nice extended Feature for outside the scope of this project | 3 | 3 | 2 | 5 | 10 | 2 | 4 | 3 | 6 | 3 | 5 | 2 | 10 |  | 5 | 1 | 5.625 | 2.7143 | 4.4211 | 4.5 | 10 | 2 | 8.8393 | 0
|  | ID |  | Given | When | Then
|  | AT | 31.1
|  | AT | 31.2
|  | AT | 31.3
|  | AT | 31.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 32 | User | be able to save a proposed schedule for later | I can leave or change my schedule and come back to it |  | 26, 46,47 | This is a nice extended Feature for outside the scope of this project | 3 | 3 | 5 | 5 | 10 | 2 | 8 | 2 | 7 | 3 | 5 | 2 | 10 |  | 7 | 2 | 6.875 | 2.7143 | 6.0526 | 6 | 10 | 3 | 6.125 | 0
|  | ID |  | Given | When | Then
|  | AT | 32.1
|  | AT | 32.2
|  | AT | 32.3
|  | AT | 32.4
|  | ID |  | AS A | I Want To | So That
| 3 | US | 33 | User | be able to load a proposed schedule | I can continue working on a schedule I started earlier |  | 26,46 , 47 | This is a nice extended Feature for outside the scope of this project | 3 | 3 | 2 | 5 | 10 | 2 | 8 | 3 | 6 | 2 | 7 | 2 | 10 |  | 5 | 2 | 6.375 | 2.7143 | 5.2105 | 5.25 | 10 | 2 | 8.8393 | 0
|  | ID |  | Given | When | Then
|  | AT | 33.1
|  | AT | 33.2
|  | AT | 33.3
|  | AT | 33.4
|  | ID |  | AS A | I Want To | So That
1 | 1 | US: | 34 | User | be able to select the term I am interested in | I can see whats offered that term |  | 46 | we could set our application to only be the current term for now, to not need this until later | 2 | 5 | 1 | 5 | 1 | 5 | 2 | 4 | 2 | 4 | 2 | 4 | 2 |  | 2 | 4 | 1.75 | 4.4286 | 1.6774 | 1.75 | 2 | 1 | 0.21429 | 1.75
|  | ID |  | Given | When | Then
|  | AT | 34.1 | the calendar view | I select a different term from the drop down menu | the calendar changes to that term
|  | AT | 34.2 | the university / term selection screen | I select a term | I am taken to my calendar for the correct term
|  | AT | 34.3
|  | AT | 34.4
SOCIAL MEDIA SHARING
|  | ID |  | AS A | I Want To | So That
| 4 | US | 35 | User | be able to share what classes I'm taking so my friends can join the same sections | I have someone else to suffer through how terrible some classes can be |  | not doing | outside scope | 10 | 1 | 5 | 3 | 10 | 2 | 8 | 1 | 10 | 1 | 15 | 1 | 10 |  | 10 | 1 | 9.75 | 1.4286 | 8.8 | 8.75 | 15 | 5 | 7.6429 | 0
|  | ID |  | Given | When | Then
|  | AT | 35.1
|  | AT | 35.2
|  | AT | 35.3
|  | AT | 35.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 36 | User | be able to see what classes my firiends are taking so I can join the same sections | I have someone else to suffer through how terrible some classes can be |  | not doing | outside scope | 10 | 1 | 5 | 2 | 10 | 2 | 8 | 1 | 10 | 1 | 15 | 1 | 10 |  | 10 | 1 | 9.75 | 1.2857 | 9.2222 | 9.25 | 15 | 5 | 7.6429 | 0
|  | ID |  | Given | When | Then
|  | AT | 36.1
|  | AT | 36.2
|  | AT | 36.3
|  | AT | 36.4
GENERAL UI REQUIREMENTS
|  | ID |  | AS A | I Want To | So That
| 1 | US | 37 | User | navigate through the app easily | I can use the app |  |  | this one is pretty vague and may be too difficult to set up tests for. (Unless we opt to just set a hard limit on the number of different navigation screens | 3 | 5 | 3 | 5 | 3 | 4 | 2 | 4 | 4 | 2 | 4 | 2 |  |  |  |  | 3.1667 | 3.6667 | 3 | 3 | 4 | 2 | 0.56667 | 0
|  | ID |  | Given | When | Then
|  | AT | 37.1 | any screen | I want to get to another screen | I am at most 2 clicks away
|  | AT | 37.2
|  | AT | 37.3
|  | AT | 37.4
|  | ID |  | AS A | I Want To | So That
| 1 | US | 38 | User | be able to read the text on my tiny phone | I can see what I'm doing |  |  |  | 3 | 5 | 2 | 5 | 3 | 4 | 2 | 4 | 2 | 5 | 1 | 4 |  |  |  |  | 2.1667 | 4.5 | 2.1852 | 2.25 | 3 | 1 | 0.56667 | 0
|  | ID |  | Given | When | Then
|  | AT | 38.1 | some text in app | user "zooms" | text is enlarged
|  | AT | 38.2 | settings page in app | user changes text size | text size is changed
|  | AT | 38.3
|  | AT | 38.4
|  | ID |  | AS A | I Want To | So That
| 2 | US | 39 | User | be able to update my settings | I can update passwords / emails. etc |  | 45 | This can be expanded to include allowing conflicts or other overrides | 3 | 5 | 3 | 4 | 5 | 2 | 5 | 3 | 3 | 3 | 2 | 3 |  |  | 5 | 1 | 3.7143 | 3 | 3.4286 | 3.5 | 5 | 2 | 1.5714 | 0
|  | ID |  | Given | When | Then
|  | AT | 39.1
|  | AT | 39.2
|  | AT | 39.3
|  | AT | 39.4
PAYMENT / SECURITY
|  | ID |  | AS A | I Want To | So That
| 3 | US | 40 | User | see the fee assessment | I know how much to pay |  |  | I see this as completely optional for now. We could assume that the client is offering it as a free service, unless told otherwise | 2 | 5 | 2 | 5 | 5 | 1 | 2 | 4 | 2 | 3 | 2 | 2 | 2 | 5 | 2 | 4 | 2.375 | 3.625 | 2.1034 | 2 | 5 | 2 | 1.125 | 0
|  | ID |  | Given | When | Then
|  | AT | 40.1
|  | AT | 40.2
|  | AT | 40.3
|  | AT | 40.4
|  | ID |  | AS A | I Want | So That
| 3 | US | 41 | User | my login / password to be kept secret from others | they can't mess with my schedule |  | 17 | for our mock up, we dont really need to worry about security | 8 | 3 | 8 | 3 | 10 | 1 | 5 | 3 | 6 | 3 | 4 | 4 | 4 | 1 | 5 | 1 | 6.25 | 2.375 | 6.1053 | 6 | 10 | 4 | 4.7857 | 0
|  | ID |  | Given | When | Then
|  | AT | 41.1
|  | AT | 41.2
|  | AT | 41.3
|  | AT | 41.4
GOOGLE MAPS INTEGRATION
|  | ID |  | AS A | I Want To | So That
| 4 | US | 42 | User | see how long a walk to expect between classes | I can plan classes that make sense |  | not doing |  | 10 | 1 | 20 | 4 | 10 | 1 | 8 | 2 | 10 | 2 | 10 | 1 | 10 |  | 7 | 1 | 10.625 | 1.7143 | 12.75 | 12.75 | 20 | 7 | 15.6964 | 0
|  | ID |  | Given | When | Then
|  | AT | 42.1
|  | AT | 42.2
|  | AT | 42.3
|  | AT | 42.4
|  | ID |  | AS A | I Want To | So That
| 4 | US | 43 | User | be notified when I have to leave for school | I make it to class on time |  | not doing |  | 3 | 5 | 4 | 5 | 2 | 2 | 8 | 2 | 5 | 2 | 5 | 1 | 10 |  | 7 | 1 | 5.5 | 2.5714 | 4.2778 | 4.25 | 10 | 2 | 7.1429 | 0
|  | ID |  | Given | When | Then
|  | AT | 43.1
|  | AT | 43.2
|  | AT | 43.3
|  | AT | 43.4
EMAIL INTEGRATION
|  | ID |  | AS A | I Want To | So That
| 4 | US | 44 | User | have an override email automatically generated | I don't have to type one myself |  | not doing |  | 6 | 3 | 2 | 5 | 1 | 5 | 5 | 3 | 5 | 2 | 10 | 1 | 10 |  | 7 | 1 | 5.75 | 2.8571 | 3.75 | 3.75 | 10 | 1 | 10.7857 | 0
|  | ID |  | Given | When | Then
|  | AT | 44.1
|  | AT | 44.2
|  | AT | 44.3
|  | AT | 44.4
Prerequisites for other User Stories
|  | ID |  | AS A | I Want To | So That
| 1 | US | 45 | User | be able to load/ save data to the phone (permissions) | I can perform any other actions requiring this feature |  |  |  | 8 | 3 | 8 | 3 | 5 | 3 | 4 | 4 | 6 | 2 | 8 | 1 |  |  | 6 | 1 | 6.4286 | 2.4286 | 6.1765 | 6.25 | 8 | 4 | 2.619 | 0
|  | ID |  | Given | When | Then
|  | ID |  | AS A | I Want To | So That
| 1 | US | 46 | User | be able to load / save data from/to a database | I can perform any other actions requiring this feature |  |  |  | 8 | 3 | 8 | 3 | 5 | 4 | 3 | 4 | 6 | 3 | 5 | 2 |  |  | 6 | 3 | 5.8571 | 3.1429 | 5.7273 | 5.75 | 8 | 3 | 3.1429 | 0
|  | ID |  | Given | When | Then
|  | ID |  | AS A | I Want To | So That
| 3 | US | 47 | User | be able to see a visual calendar (not just text based) | I can perform any other actions requiring this feature |  |  |  | 10 | 3 | 10 | 3 | 3 | 4 | 10 | 2 | 10 | 2 | 8 | 2 | 10 | 2 | 8 | 2 | 8.625 | 2.5 | 8.2 | 8.25 | 10 | 3 | 5.9821 | 0
|  | ID |  | Given | When | Then
TEMPLATE FOR ADDING MORE USER STORIES
|  | ID |  | AS A | I Want To | So That
|  | US | 45 | User
|  | ID |  | Given | When | Then
|  | AT | 45.1
|  | AT | 45.2
|  | AT | 45.3
|  | AT | 45.4

## Tasks
Pair | US | summary | Not Applicable | Make | Junit | Espresso
Andre | 28, 29 | be able to login |  | 30 min | 1 hour | 1.5 hours
Paul |  | Create a user |  |  | same | smae
Mitchell | 2018-12-13 | Course Database | Saturday
Troy |  | Java Object representing database -> Array(list) of dictionarys. This might change. Dictionarys might be to space intensive. | Saturday " + 1-2 Days"
Jayden | 18, 23 | add and drop a course
Samantha |  | helping Jayden
Max | 12,13,34 | Show all courses for that term (with spots left)
Faye |  | Select a term

## Questions To Ask
ID | Item | Question | TA Response
US 12 | View Course Info | Do we need any sorting ability by default, or in an exhaustive list okay to start | up to us
US 13 | be able to see how many spots remain in a course | Can this just be shown along with either general course info and/or detailed course info? | up to us
US 15 | be notified if there is a conflict between my selected courses | Do you only need this as you try to register? Can we make conflicts unselectable entirely? | up to us
US 18 | register for a course | Do we need to actually login to Dal and register, or just mark the class as registered in our system and then later add it to the calendar when that is operational? | Obviously we don't since the project has nothing to do with Dal
US 18 | register for a course | do we have to be able to recall what you registered for on a future running / login | up to us
US 26 | be able to see my weekly schedule | Do you need an actual visual calendar, or is say a table with 5 columns for days and then text stating the class / time/ details in chronological order sufficient. IE do you need a complete GUI just like google calendar? | up to us

## Discussion Points
ID | Item | Discussion Point
US 10, US 14 | Be able to view my favorited classes | This requires a Many-to-Many table. Probably change to OoS(4)
US 16 | be abe to overide the conflict message | Default behavour for Dalhousie is to ignore time conflicts. This should not be OoS(4) If US 15 is M(0) then this should be too.
US 28, US 29 | be able to create an account | Why? Students should use their dal account. -> US 17 | This was primarily so they can save and load their proposed schedules, if we make that option.
US 30 | be able to add a course to my calendar without registering for it | Backend table modification, or new table. Possibly OoS(4)
US 37, US 38 | navigate through the app easily, be able to read on my tiny phone | I think this is not a user case because I think it has to be done while we are coding the UI | fair point Agree also, but are we going to have a section/place for developer stories? Then again, this is an issue that effects users.

## Just a Place Holder
Other ideas to add
auto lab / tutorial adding
fix lab drop issue
alternative arrangements of courses
show prerequisites / corequisites
show completed courses.
suggest courses based on completed preprequisites or current corequisites
color code almost full classes (or historically full classes)
show alternative lab times / course times
max number of login trials
I can spare 3-6 hours per week for project work. I expect about the same from each group memeber.
Working in pairs, we should be able to get a good 12-15 hours of work over a 3 week period.
4 pairs means 48-60 hours of work in total assuming everyone is pulling their weight.
Let's maybe set our target at 54 hours for iteration 1. It includes exam time, but it also includes reading week.
That's 18 blocks of work for our velocity
| M | T | W | T | F | S | S
| 24 | 24 | 24 | 24 | 24 | 24 | 24
Sleep | 8 | 8 | 8 | 8 | 8 | 8 | 8
Meal Prep & eating | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cleaning & maintenance | 1 | 1 | 1 | 1 | 1 | 1 | 1
Chores | 1 | 1 | 1 | 1 | 1 | 1 | 1
Transportation | 2 | 2 | 2 | 2 | 2 | 2 | 2
Class time | 3 | 3 | 3 | 3 | 3 | 0 | 0
Labs / Tutorials | 2 | 2 | 2 | 2 | 2 | 0 | 0
sub total left | 5 | 5 | 5 | 5 | 5 | 10 | 10
That leavs 45 hours a week, or 9 hours a class assuming you dont allow time for work, 4 hours a class if you do.
Assignments | 3
Studying (Notes) | 1
Projects | 4 | we shouldn't be planning any more than this a week if you are in 5 courses worth of classes.
Exams Studying | 1